## Sheet1
Task ID | Phase | Task Name | Add to OnePager | Start Date | Finish Date | Resource Names | % Complete
1 | Idea Generation | SWOT Analysis | Yes | 2018-01-05 | 2018-02-15 | Product Team | 10%
2 | Idea Generation | Brainstorming | Yes | 2018-02-16 | 2018-04-19 | Product Team | 20%
3 | Idea Screening | Customer Analysis | Yes | 2018-04-20 | 2018-05-31 | Sales Team | 33%
4 | Idea Screening | Market Analysis | Yes | 2018-04-20 | 2018-06-21 | Sales Team | 48%
5 | Idea Screening | Competitive Analysis | Yes | 2018-06-22 | 2018-08-02 | Sales Team | 44%
6 | Idea Screening | Technical Feasibility | Yes | 2018-04-20 | 2018-07-12 | Engineering Team | 36%
7 | Idea Screening | Finalize Idea Selection | Yes | 2018-08-03 | 2018-08-03 | Product Team | 55%
8 | Concept Development/Testing | Intellectual Property Search | Yes | 2018-08-06 | 2018-12-07 | Legal Team | 77%
9 | Concept Development/Testing | Feature Specifications | Yes | 2018-08-06 | 2019-01-18 | Product Team | 10%
10 | Concept Development/Testing | Rapid Prototyping | Yes | 2019-01-21 | 2019-03-22 | Engineering Team | 20%
11 | Concept Development/Testing | Production Optimization Analysis | Yes | 2019-01-21 | 2019-03-01 | Operations Team | 32%
12 | Concept Development/Testing | Concept Testing | Yes | 2019-03-25 | 2019-06-14 | QA Team | 33%
13 | Business Analysis | Pricing Analysis | Yes | 2018-08-06 | 2018-10-05 | Product Team | 66%
14 | Business Analysis | Sales Forecasting | Yes | 2018-10-08 | 2018-11-16 | Sales Team | 8%
15 | Business Analysis | Break-Even Analysis | Yes | 2018-11-19 | 2018-12-07 | Product Team | 88%
16 | Beta Testing/Market Testing | Beta Production Run | Yes | 2019-06-17 | 2019-07-26 | Operations Team | 99%
17 | Beta Testing/Market Testing | Internal Testing | Yes | 2019-07-29 | 2019-10-18 | QA Team | 10%
18 | Beta Testing/Market Testing | Focus Group Interviews | Yes | 2019-06-17 | 2019-09-27 | Product Team | 20%
19 | Beta Testing/Market Testing | Determine Necessary Adjustments | Yes | 2019-10-21 | 2019-11-29 | Product Team | 32%
20 | Beta Testing/Market Testing | Initial Production Run for Test Market | Yes | 2019-12-02 | 2020-02-21 | Operations Team | 33%
21 | Beta Testing/Market Testing | Market Testing | Yes | 2020-02-24 | 2020-08-07 | Product Team | 11%
22 | Technical Implementation | New Program Initiation | Yes | 2019-06-17 | 2019-09-06 | Product Team | 10%
23 | Technical Implementation | Quality Management System | Yes | 2019-09-09 | 2019-10-18 | QA Team | 20%
24 | Technical Implementation | Operations Planning | Yes | 2019-09-09 | 2019-11-29 | Operations Team | 32%
25 | Technical Implementation | Supplier Collaboration | Yes | 2019-09-09 | 2019-11-29 | Sales Team | 33%
26 | Technical Implementation | Logistics Plan | Yes | 2019-12-02 | 2020-01-10 | Operations Team | 22%
27 | Technical Implementation | Contingency Planning | Yes | 2020-01-13 | 2020-01-31 | Operations Team | 33%
28 | Commercialization (Post-NPD) | Distributor Negotiations | Yes | 2020-08-10 | 2021-01-22 | Legal Team | 10%
29 | Commercialization (Post-NPD) | Marketing & Advertising Campaigns | Yes | 2020-08-10 | 2020-12-11 | Sales Team | 20%
30 | Commercialization (Post-NPD) | Product Launch | Yes | 2021-01-25 | 2021-01-25 | Product Team | 32%
31 | Commercialization (Post-NPD) | Begin Distribution | Yes | 2021-01-25 | 2021-01-25 | Product Team | 33%