## Sheet1
ID | Task Name | Start | Finish | Status | Backlog Category | Task Board | Sprint
1 | Sprint 1
2 | Quoting App
3 | Email Button | 2022-04-04 | 2022-04-22 | Locked | Quoting App | Yes | Sprint 1
4 | Setup Wizard | 2022-04-04 | 2022-04-22 | Locked | Quoting App | Yes | Sprint 1
5 | Clone Quote | 2022-04-04 | 2022-04-22 | Locked | Quoting App | Yes | Sprint 1
6 | Auto-Fill | 2022-04-04 | 2022-04-22 | Locked | Quoting App | Yes | Sprint 1
7 | Fulfillment
8 | Custom View Tab | 2022-04-04 | 2022-04-22 | Locked | Fulfillment | Yes | Sprint 1
9 | Sort Orders | 2022-04-04 | 2022-04-22 | Locked | Fulfillment | Yes | Sprint 1
10 | Filter Orders | 2022-04-04 | 2022-04-22 | Locked | Fulfillment | Yes | Sprint 1
11 | Auto-email | 2022-04-04 | 2022-04-22 | Locked | Fulfillment | Yes | Sprint 1
12 | Datamart
13 | Report Server Upgrade | 2022-04-04 | 2022-04-22 | Locked | Datamart | Yes | Sprint 1
14 | My Reports View | 2022-04-04 | 2022-04-22 | Locked | Datamart | Yes | Sprint 1
15 | Sales by Week/Resource | 2022-04-04 | 2022-04-22 | Locked | Datamart | Yes | Sprint 1
16 | Workflow
17 | Auto-queue | 2022-04-04 | 2022-04-22 | Locked | Workflow | Yes | Sprint 1
18 | Auto-assign | 2022-04-04 | 2022-04-22 | Locked | Workflow | Yes | Sprint 1
19 | Email Reminder | 2022-04-04 | 2022-04-22 | Locked | Workflow | Yes | Sprint 1
20 | Billing
21 | Product Reconcile | 2022-04-04 | 2022-04-22 | Locked | Billing | Yes | Sprint 1
22 | Tax System Upgrade | 2022-04-04 | 2022-04-22 | Locked | Billing | Yes | Sprint 1
23 | Sox Audit 1 | 2022-04-04 | 2022-04-22 | Locked | Billing | Yes | Sprint 1
24 | Sprint 2
25 | Quoting App
26 | Multi-quote | 2022-04-25 | 2022-05-13 | Funded | Quoting App | Yes | Sprint 2
27 | Auto-remind | 2022-04-25 | 2022-05-13 | Prioritized | Quoting App | Yes | Sprint 2
28 | Product-suggest | 2022-04-25 | 2022-05-13 | Funded | Quoting App | Yes | Sprint 2
29 | Undo-fill | 2022-04-25 | 2022-05-13 | Prioritized | Quoting App | Yes | Sprint 2
30 | Fulfillment
31 | Multi-window | 2022-04-25 | 2022-05-13 | Submitted | Fulfillment | Yes | Sprint 2
32 | Supp Order | 2022-04-25 | 2022-05-13 | Funded | Fulfillment | Yes | Sprint 2
33 | Vendor-suggest | 2022-04-25 | 2022-05-13 | Submitted | Fulfillment | Yes | Sprint 2
34 | Auto-discovery | 2022-04-25 | 2022-05-13 | Prioritized | Fulfillment | Yes | Sprint 2
35 | Workflow
36 | Auto-kickback | 2022-04-25 | 2022-05-13 | Funded | Workflow | Yes | Sprint 2
37 | Auto-prioritize | 2022-04-25 | 2022-05-13 | Funded | Workflow | Yes | Sprint 2
38 | Aging Alerts | 2022-04-25 | 2022-05-13 | Prioritized | Workflow | Yes | Sprint 2
39 | Billing
40 | Download PDF | 2022-04-25 | 2022-05-13 | Submitted | Billing | Yes | Sprint 2
41 | Search by Invoice | 2022-04-25 | 2022-05-13 | Funded | Billing | Yes | Sprint 2
42 | Commissions Upgrade | 2022-04-25 | 2022-05-13 | Funded | Billing | Yes | Sprint 2
43 | Portal
44 | Invoice Lookup | 2022-04-25 | 2022-05-13 | Submitted | Portal | Yes | Sprint 2
45 | Request Status | 2022-04-25 | 2022-05-13 | Funded | Portal | Yes | Sprint 2
46 | Contact Databbase | 2022-04-25 | 2022-05-13 | Funded | Portal | Yes | Sprint 2
47 | Sprint 3
48 | Quoting App
49 | Quote Wizard | 2022-05-16 | 2022-06-03 | Requested | Quoting App | Yes | Sprint 3
50 | Customer Auto-quote | 2022-05-16 | 2022-06-03 | Requested | Quoting App | Yes | Sprint 3
51 | Contract Tool | 2022-05-16 | 2022-06-03 | Requested | Quoting App | Yes | Sprint 3
52 | Custom Home Page | 2022-05-16 | 2022-06-03 | Requested | Quoting App | Yes | Sprint 3
53 | Billing
54 | Enhance Logo | 2022-05-16 | 2022-06-03 | Requested | Billing | Yes | Sprint 3
55 | Change Billing Address | 2022-05-16 | 2022-06-03 | Requested | Billing | Yes | Sprint 3
56 | Tax Page Organization | 2022-05-16 | 2022-06-03 | Requested | Billing | Yes | Sprint 3
57 | Portal
58 | Customer Home Page | 2022-05-16 | 2022-06-03 | Requested | Portal | Yes | Sprint 3
59 | Auto-notify | 2022-05-16 | 2022-06-03 | Requested | Portal | Yes | Sprint 3
60 | Ticket Lookup | 2022-05-16 | 2022-06-03 | Requested | Portal | Yes | Sprint 3
61 | Inventory
62 | Field Audit | 2022-05-16 | 2022-06-03 | Requested | Inventory | Yes | Sprint 3
63 | RFP | 2022-05-16 | 2022-06-03 | Requested | Inventory | Yes | Sprint 3
64 | Drag/Drop Location | 2022-05-16 | 2022-06-03 | Requested | Inventory | Yes | Sprint 3
65 | Multi-Tier | 2022-05-16 | 2022-06-03 | Requested | Inventory | Yes | Sprint 3
66 | Middleware
67 | Bus Upgrade | 2022-05-16 | 2022-06-03 | Requested | Middleware | Yes | Sprint 3
68 | Memory Enhancement | 2022-05-16 | 2022-06-03 | Requested | Middleware | Yes | Sprint 3
69 | Multi-threading | 2022-05-16 | 2022-06-03 | Requested | Middleware | Yes | Sprint 3