## Integrated Milestone Plan
Task Name | Duration | Start Date | End Date | Color | Shape | Predecessors | Add to OnePager | % Complete | Summary | Status | Assigned To | Comments | Start | Finish | Flag20 | Text29 | Text30 | Outline Level
Summary | 586d | 2019-02-28 | 2021-05-27 |  |  |  |  | 0% | Yes | [8 empty] | 1
Major Milestones | 386d | 2019-12-04 | 2021-05-27 |  |  |  |  | 0% | Yes | [8 empty] | 2
M1 | 0 | 2019-12-04 | 2019-12-04 | Red | Arrow | 52 | TRUE | 100% | No | [5 empty] | TRUE | Red | Arrow | 3
M2 | 0 | 2020-09-17 | 2020-09-17 | Red | Arrow | 53 | TRUE | 0% | No | [5 empty] | TRUE | Red | Arrow | 3
Launch | 0 | 2021-05-27 | 2021-05-27 | Blue | Rocket | 64FS +30d | TRUE | 0% | No | [5 empty] | TRUE | Blue | Rocket | 3
Phase Gates | 423d | 2019-02-28 | 2020-10-12 |  |  |  |  | 0% | Yes | [8 empty] | 2
Phase 1 | 123d | 2019-02-28 | 2019-08-19 | Red |  |  | TRUE | 0% | No | Yes |  |  |  |  | TRUE | Red |  | 3
Milestone | 123d | 2019-02-28 | 2019-08-19
P1.1 | 0 | 2019-03-01 | 2019-03-01 | Red | Arrow |  | TRUE | 100% | Yes | [5 empty] | TRUE | Red | Arrow | 4
P1.2 | 0 | 2019-05-24 | 2019-05-24 | Red | Arrow | 9FS +60d | TRUE | 100% | Yes | [5 empty] | TRUE | Red | Arrow | 4
P1.3 | 0 | 2019-08-16 | 2019-08-16 | Red | Arrow | 10FS +60d | TRUE | 100% | Yes | [5 empty] | TRUE | Red | Arrow | 4
Phase 2 | 124d | 2019-09-25 | 2020-03-16 | Green |  |  | TRUE | 0% | No | [5 empty] | TRUE | Green |  | 3
Milestone | 124d | 2019-09-25 | 2020-03-16
P2.1 | 0 | 2019-09-27 | 2019-09-27 | Green | Arrow | 11FS +30d | TRUE | 100% | Yes | [5 empty] | TRUE | Green | Arrow | 4
P2.2 | 0 | 2019-12-20 | 2019-12-20 | Green | Arrow | 14FS +60d | TRUE | 100% | Yes | [5 empty] | TRUE | Green | Arrow | 4
P2.3 | 0 | 2020-03-13 | 2020-03-13 | Green | Arrow | 15FS +60d | TRUE | 100% | Yes | [5 empty] | TRUE | Green | Arrow | 4
Phase 3 | 124d | 2020-04-22 | 2020-10-12 | Blue |  |  | TRUE | 0% | No | [5 empty] | TRUE | Blue |  | 3
Milestone | 124d | 2020-04-22 | 2020-10-12
P3.1 | 0 | 2020-04-24 | 2020-04-24 | Blue | Arrow | 16FS +30d | TRUE | 0% | Yes | [5 empty] | TRUE | Blue | Arrow | 4
P3.2 | 0 | 2020-07-17 | 2020-07-17 | Blue | Arrow | 19FS +60d | TRUE | 0% | Yes | [5 empty] | TRUE | Blue | Arrow | 4
P3.3 | 0 | 2020-10-09 | 2020-10-09 | Blue | Arrow | 20FS +60d | TRUE | 0% | Yes | [5 empty] | TRUE | Blue | Arrow | 4
Detail | 579d | 2019-01-28 | 2021-04-15 |  |  |  |  | 61% | Yes | [8 empty] | 1
GETs | 162d | 2019-01-28 | 2019-09-11 |  |  |  |  | 100% | Yes | [8 empty] | 2
GET-1 | 0 | 2019-01-28 | 2019-01-28 | Red | Triangle |  | TRUE | 100% | No | [5 empty] | TRUE | Red | Triangle | 3
GET-2 | 0 | 2019-03-28 | 2019-03-28 | Orange | Triangle |  | TRUE | 100% | No | [5 empty] | TRUE | Orange | Triangle | 3
GET-3 | 0 | 2019-05-15 | 2019-05-15 | Blue | Triangle |  | TRUE | 100% | No | [5 empty] | TRUE | Blue | Triangle | 3
GET-4 | 0 | 2019-07-01 | 2019-07-01 | Purple | Triangle |  | TRUE | 100% | No | [5 empty] | TRUE | Purple | Triangle | 3
GET-5 | 0 | 2019-09-11 | 2019-09-11 | Green | Triangle |  | TRUE | 100% | No | [5 empty] | TRUE | Green | Triangle | 3
ARCs | 162d | 2019-01-28 | 2019-09-11 |  |  |  |  | 100% | Yes | [8 empty] | 2
ARC-1 | 0 | 2019-01-28 | 2019-01-28 | Red | Triangle | 24 | TRUE | 100% | No | [5 empty] | TRUE | Red | Triangle | 3
ARC-2 | 0 | 2019-03-28 | 2019-03-28 | Orange | Triangle | 25 | TRUE | 100% | No | [5 empty] | TRUE | Orange | Triangle | 3
ARC-3 | 0 | 2019-05-15 | 2019-05-15 | Blue | Triangle | 26 | TRUE | 100% | No | [5 empty] | TRUE | Blue | Triangle | 3
ARC-4 | 0 | 2019-07-15 | 2019-07-15 | Purple | Triangle | 27FS +10d | TRUE | 100% | No | [5 empty] | TRUE | Purple | Triangle | 3
ARC-5 | 0 | 2019-09-11 | 2019-09-11 | Green | Triangle | 28 | TRUE | 100% | No | [5 empty] | TRUE | Green | Triangle | 3
CLBs | 161d | 2019-01-31 | 2019-09-13 |  |  |  |  | 100% | Yes | [8 empty] | 2
CLB-1 | 0 | 2019-01-31 | 2019-01-31 | Red | Triangle | 30FS +3d | TRUE | 100% | No | [5 empty] | TRUE | Red | Triangle | 3
CLB-2 | 0 | 2019-04-08 | 2019-04-08 | Orange | Triangle | 31FS +7d | TRUE | 100% | No | [5 empty] | TRUE | Orange | Triangle | 3
CLB-3 | 0 | 2019-05-24 | 2019-05-24 | Blue | Triangle | 32FS +7d | TRUE | 100% | No | [5 empty] | TRUE | Blue | Triangle | 3
CLB-4 | 0 | 2019-07-22 | 2019-07-22 | Purple | Triangle | 33FS +5d | TRUE | 100% | No | [5 empty] | TRUE | Purple | Triangle | 3
CLB-5 | 0 | 2019-09-13 | 2019-09-13 | Green | Triangle | 34FS +2d | TRUE | 100% | No | [5 empty] | TRUE | Green | Triangle | 3
WMNs | 191d | 2019-02-14 | 2019-11-08 |  |  |  |  | 100% | Yes | [8 empty] | 2
WMN-1 | 0 | 2019-02-14 | 2019-02-14 | Red | Triangle | 36FS +10d | TRUE | 100% | No | [5 empty] | TRUE | Red | Triangle | 3
WMN-2 | 0 | 2019-04-29 | 2019-04-29 | Orange | Triangle | 37FS +15d | TRUE | 100% | No | [5 empty] | TRUE | Orange | Triangle | 3
WMN-3 | 0 | 2019-06-21 | 2019-06-21 | Blue | Triangle | 38FS +20d | TRUE | 100% | No | [5 empty] | TRUE | Blue | Triangle | 3
WMN-4 | 0 | 2019-09-02 | 2019-09-02 | Purple | Triangle | 39FS +30d | TRUE | 100% | No | [5 empty] | TRUE | Purple | Triangle | 3
WMN-5 | 0 | 2019-11-08 | 2019-11-08 | Green | Triangle | 40FS +40d | TRUE | 100% | No | [5 empty] | TRUE | Green | Triangle | 3
Buildouts | 326d | 2019-02-14 | 2020-05-14 |  |  |  |  | 75% | Yes | [8 empty] | 2
BLD-A | 90d | 2019-02-14 | 2019-06-19 | Red |  | 42, 43FF | TRUE | 100% | No | [5 empty] | TRUE | Red |  | 3
BLD-B | 75d | 2019-08-02 | 2019-11-14 | Blue |  | 44FS +30d, 45FF | TRUE | 100% | No | [5 empty] | TRUE | Blue |  | 3
BLD-C | 90d | 2020-01-10 | 2020-05-14 | Green |  | 46FS +45d | TRUE | 30% | No | [5 empty] | TRUE | Green |  | 3
Deliveries | 326d | 2019-06-20 | 2020-09-17 |  |  |  |  | 57% | Yes | [8 empty] | 2
DLV-A | 120d | 2019-06-20 | 2019-12-04 | Red |  | 48 | TRUE | 100% | No | [5 empty] | TRUE | Red |  | 3
DLV-B | 90d | 2020-05-15 | 2020-09-17 | Blue |  | 49, 50 | TRUE | 0% | No | [5 empty] | TRUE | Blue |  | 3
Checkpoints | 326d | 2019-06-20 | 2020-09-17 |  |  |  |  | 0% | Yes | [8 empty] | 2
CP A-1 | 0 | 2019-06-20 | 2019-06-20 | Red | Triangle | 52SS | TRUE | 100% | No | [5 empty] | TRUE | Red | Triangle | 3
CP A-2 | 0 | 2019-12-04 | 2019-12-04 | Red | Triangle | 52FF | TRUE | 0% | No | [5 empty] | TRUE | Red | Triangle | 3
CP B-1 | 0 | 2020-05-15 | 2020-05-15 | Red | Triangle | 53SS | TRUE | 0% | No | [5 empty] | TRUE | Red | Triangle | 3
CP B-2 | 0 | 2020-09-17 | 2020-09-17 | Red | Triangle | 53FF | TRUE | 0% | No | [5 empty] | TRUE | Red | Triangle | 3
Launch Preparedness | 150d | 2020-09-17 | 2021-04-15 |  |  |  |  | 0% | Yes | [8 empty] | 2
LP-1 | 0 | 2020-09-17 | 2020-09-17 | Red | Diamond | 55, 56, 57, 58 | TRUE | 0% | No | [5 empty] | TRUE | Red | Diamond | 3
LP-2 | 0 | 2020-10-29 | 2020-10-29 | Red | Diamond | 60FS +30d | TRUE | 0% | No | [5 empty] | TRUE | Red | Diamond | 3
LP-3 | 0 | 2020-12-10 | 2020-12-10 | Blue | Diamond | 61FS +30d | TRUE | 0% | No | [5 empty] | TRUE | Blue | Diamond | 3
LP-4 | 0 | 2021-02-04 | 2021-02-04 | Blue | Diamond | 62FS +40d | TRUE | 0% | No | [5 empty] | TRUE | Blue | Diamond | 3
LP-5 | 0 | 2021-04-15 | 2021-04-15 | Green | Diamond | 63FS +50d | TRUE | 0% | No | [5 empty] | TRUE | Green | Diamond | 3