## Sheet1
ID | Task Name | Start | Finish | Baseline Start | Baseline Finish | % Complete | Status | Programs
1 | Launch Support Programs | 2024-06-03 | 2025-03-07 | 2024-06-03 | 2025-03-07 | 100% | Complete | Program Timelines
2 | AF Launch Support Program | 2024-06-03 | 2024-09-20 | 2024-06-03 | 2024-09-20 | 100% | Complete | Program Timelines
3 | NASA Launch Support Program | 2024-08-26 | 2024-12-13 | 2024-08-26 | 2024-12-13 | 100% | Complete | Program Timelines
4 | Other Launch Support Program | 2024-11-18 | 2025-03-07 | 2024-11-18 | 2025-03-07 | 100% | Complete | Program Timelines
5 | On Orbit Support Program | 2024-12-30 | 2026-12-25 | 2024-12-30 | 2026-10-25 | 5% | Late | Program Timelines
6 | AF Missions Support | 2025-09-22 | 2026-02-06 | 2025-09-22 | 2026-02-06 | 0% | Future Task | COMM Team
7 | NASA Missions Support Projects | 2024-12-30 | 2025-07-21 | 2024-12-30 | 2025-05-18 | 20% | Late | DS-1 Team
8 | Other Missions Support Projects | 2026-08-09 | 2026-12-25 | 2026-07-12 | 2026-10-31 | 0% | Future Task | DS-2 Team
9 | Vehicle RS-205 Launch Support Project | 2024-06-03 | 2024-08-23 | 2024-06-03 | 2024-08-23 | 100% | Complete | RE-1 Team
10 | AE-5 Launch Support Project | 2024-08-26 | 2024-11-15 | 2024-08-26 | 2024-11-15 | 100% | Complete | RE-1 Team
11 | X-566 Launch Support Project | 2024-11-18 | 2025-02-07 | 2024-11-18 | 2025-03-18 | 100% | Complete | RE-1 Team
12 | Vehicle WQ-5 Launch Support Project | 2024-07-01 | 2024-09-20 | 2024-07-01 | 2024-09-20 | 100% | Complete | RE-2 Team
13 | AE-6 Launch Support Project | 2024-09-23 | 2024-12-13 | 2024-09-23 | 2024-12-13 | 100% | Complete | RE-2 Team
14 | K-45 Launch Support Project | 2024-12-16 | 2025-03-07 | 2024-12-16 | 2025-03-07 | 100% | Complete | RE-2 Team