## Master Program Schedule
Task Name | Duration | Start Date | End Date | Column16 | Predecessors | % Complete | Status | Assigned To | Comments | Master Program Schedule (Flag 9) | Text30 | Show All Summary | Show Rocket Prop Pgms | Cost | Actual Cost
Rocket Propulsion Programs | 950d | 2024-08-12 | 2028-03-31 |  |  | 57% | [5 empty] | TRUE | TRUE | 240000 | 149480
RE-1 Launch Vehicle Production Program | 290d | 2024-08-12 | 2025-09-19 | On Track |  | 100% |  |  |  | TRUE | On Track |  | TRUE | 68000 | 68000
RE-1 First Stage Production Project | 150d | 2024-08-12 | 2025-03-07 |  |  | 100% |  | RE-1 Team |  |  |  |  | TRUE | 20000 | 20000
RE-1 Second Stage Production Project | 100d | 2024-12-30 | 2025-05-16 |  | 3SS +100d | 100% |  | RE-1 Team |  |  |  |  | TRUE | 25000 | 25000
RE-1 Stage Integration and Test Project | 90d | 2025-05-19 | 2025-09-19 |  | 3, 4 | 100% |  | RE-1 Team |  |  |  |  | TRUE | 23000 | 23000
RE-2 Launch Vehicle R&D Program | 800d | 2025-03-10 | 2028-03-31 | On Track |  | 41% |  |  |  | TRUE | On Track | TRUE | TRUE | 172000 | 81480
RE-2 First Stage R&D Project | 200d | 2025-03-10 | 2025-12-12 |  | 3SS +150d | 100% |  | RE-2 Team |  |  |  |  | TRUE | 42000 | 42000
RE-2 Second Stage R&D Project | 200d | 2025-07-28 | 2026-05-01 |  | 7SS +100d | 84% |  | RE-2 Team |  |  |  |  | TRUE | 47000 | 39480
RE-2 Stage Component Development Project | 400d | 2026-05-04 | 2027-11-12 |  | 7, 8 | 0% |  | RE-2 Team |  |  |  |  | TRUE | 42000 | 0
RE-2 Transition to Production Project | 100d | 2027-11-15 | 2028-03-31 |  | 9 | 0% |  | RE-1 Team |  |  |  |  | TRUE | 41000 | 0
Spacecraft Programs | 820d | 2024-12-30 | 2028-02-18 |  |  | 44% | [5 empty] | TRUE |  | 1409488 | 706573.34
Communications Satellite Programs | 700d | 2024-12-30 | 2027-09-03 |  |  | 51% | [5 empty] | TRUE |  | 267112 | 179090
COMM-5 Production Program | 190d | 2024-12-30 | 2025-09-19 | On Track |  | 100% |  |  |  | TRUE | On Track | TRUE |  | 134000 | 134000
COMM-5 Component Testing and Installation Project | 100d | 2024-12-30 | 2025-05-16 |  | 3SS +100d | 100% |  | COMM Team | [5 empty] | 35000 | 35000
COMM-5 Acceptance Testing Project | 40d | 2025-05-19 | 2025-07-11 |  | 14 | 100% |  | COMM Team | [5 empty] | 42000 | 42000
COMM-5 Delivery to Customer and Customer Testing Support Project | 20d | 2025-07-14 | 2025-08-08 |  | 15 | 100% |  | COMM Team | [5 empty] | 25000 | 25000
COMM-5 Satellite and Launch Vehicle Integration and Test Project | 30d | 2025-08-11 | 2025-09-19 |  | 16 | 100% |  | COMM-5 Team | [5 empty] | 32000 | 32000
COMM-6 Development Program | 600d | 2025-05-19 | 2027-09-03 | Issues |  | 36% |  |  |  | TRUE | Issues | TRUE |  | 133112 | 45090
COMM-6 Requirements Development, Design, and Approval Project | 100d | 2025-05-19 | 2025-10-03 |  | 14SS +100d | 100% | [7 empty] | 15000 | 15000
COMM-6 Component Contracting and Development Project | 200d | 2025-10-06 | 2026-07-10 |  | 19 | 59% |  | COMM Team | [5 empty] | 51000 | 30090
COMM-6 Component Fabrication and Integration Project | 200d | 2026-07-13 | 2027-04-16 |  | 20 | 0% |  | COMM Team | [5 empty] | 42051 | 0
COMM-6 Integration and Testing Project | 100d | 2027-04-19 | 2027-09-03 |  | 21 | 0% |  | COMM Team | [5 empty] | 25061 | 0
Weather Satellite Programs | 700d | 2025-01-27 | 2027-10-01 |  |  | 47% | [5 empty] | TRUE |  | 485046 | 290149.76
WEATHER-6 Satellite Delivery Program | 160d | 2025-01-27 | 2025-09-05 | On Track |  | 100% |  |  |  | TRUE | On Track | TRUE |  | 215610 | 215610
WEATHER-6 Integration Testing Project | 100d | 2025-01-27 | 2025-06-13 |  | 14SS +20d | 100% |  | WEATHER Team | [5 empty] | 87400 | 87400
WEATHER-6 Transportation and Integration with Launch Vehicle Project | 20d | 2025-06-16 | 2025-07-11 |  | 25 | 100% |  | WEATHER Team | [5 empty] | 75802 | 75802
WEATHER-6 Prelaunch Support Project | 40d | 2025-07-14 | 2025-09-05 |  | 26 | 100% |  | WEATHER Team | [5 empty] | 52408 | 52408
WEATHER-7 R&D Program | 600d | 2025-06-16 | 2027-10-01 | Blocked |  | 33% |  |  |  | TRUE | Blocked | TRUE |  | 269436 | 74539.76
WEATHER-7 Requirements Development, Design, and Approval Project | 100d | 2025-06-16 | 2025-10-31 |  | 25 | 100% |  | WEATHER Team | [5 empty] | 26508 | 26508
WEATHER-7 Component Contracting and Development Project | 200d | 2025-11-03 | 2026-08-07 |  | 29 | 49% |  | WEATHER Team | [5 empty] | 98024 | 48031.76
WEATHER-7 Component Fabrication and Integration Project | 200d | 2026-08-10 | 2027-05-14 |  | 30 | 0% |  | WEATHER Team | [5 empty] | 86502 | 0
WEATHER-7 Integration and Testing Project | 100d | 2027-05-17 | 2027-10-01 |  | 31 | 0% |  | WEATHER Team | [5 empty] | 58402 | 0
Deep Space Missions Programs | 720d | 2025-05-19 | 2028-02-18 |  |  | 34% | [5 empty] | TRUE |  | 657330 | 237333.58
SUNSPOT Mission Program (NASA) | 320d | 2025-05-19 | 2026-08-07 | On Track |  | 68% |  |  |  | TRUE | On Track | TRUE |  | 306595 | 153003.6
SUNSPOT Mission Component Testing and Installation Project | 100d | 2025-05-19 | 2025-10-03 |  | 14 | 100% |  | DS-1 Team | [5 empty] | 35089 | 35089
SUNSPOT Mission Acceptance Testing Project | 100d | 2025-10-06 | 2026-02-20 |  | 35 | 100% |  | DS-1 Team | [5 empty] | 89402 | 89402
SUNSPOT Mission Delivery to Customer and Customer Testing Support Project | 60d | 2026-02-23 | 2026-05-15 |  | 36 | 30% |  | DS-1 Team | [5 empty] | 95042 | 28512.6
SUNSPOT Mission Satellite and Launch Vehicle Integration and Test Project | 60d | 2026-05-18 | 2026-08-07 |  | 37 | 0% |  | DS-1 Team | [5 empty] | 87062 | 0
ASTEROID PHOTO Mission Program (NASA) | 600d | 2025-11-03 | 2028-02-18 | On Track |  | 16% |  |  |  | TRUE | On Track | TRUE |  | 350735 | 84329.98
ASTEROID PHOTO Mission Requirements Development, Design, and Approval Project | 100d | 2025-11-03 | 2026-03-20 |  | 29 | 98% |  | DS-2 Team | [5 empty] | 86051 | 84329.98
ASTEROID PHOTO Mission Component Contracting and Development Project | 200d | 2026-03-23 | 2026-12-25 |  | 40 | 0% |  | DS-2 Team | [5 empty] | 105042 | 0
ASTEROID PHOTO Mission Component Fabrication and Integration Project | 200d | 2026-12-28 | 2027-10-01 |  | 41 | 0% |  | DS-2 Team | [5 empty] | 85034 | 0
ASTEROID PHOTO Mission Integration and Testing Project | 100d | 2027-10-04 | 2028-02-18 |  | 42 | 0% |  | DS-2 Team | [5 empty] | 74608 | 0
Launch Support Programs | 650d | 2026-01-12 | 2028-07-07 |  |  | 7% | [5 empty] | TRUE |  | 1030639 | 143610.35
AF Launch Support Program | 80d | 2026-01-12 | 2026-05-01 | On Track |  | 64% |  |  |  |  | On Track | TRUE |  | 215650 | 143610.35
Vehicle RS-205 Launch Support Project | 60d | 2026-01-12 | 2026-04-03 |  | 29FS +50d | 80% |  | RE-1 Team | [5 empty] | 128045 | 102436
Vehicle WQ-5 Launch Support Project | 60d | 2026-02-09 | 2026-05-01 |  | 46SS +20d | 47% |  | RE-2 Team | [5 empty] | 87605 | 41174.35
NASA Launch Support Program | 80d | 2026-04-06 | 2026-07-24 | On Track |  | 0% |  |  |  | TRUE | On Track | TRUE |  | 283755 | 0
AE-5 Launch Support Project | 60d | 2026-04-06 | 2026-06-26 |  | 46 | 0% |  | RE-1 Team | [5 empty] | 158047 | 0
AE-6 Launch Suport Project | 60d | 2026-05-04 | 2026-07-24 |  | 49SS +20d | 0% |  | RE-2 Team | [5 empty] | 125708 | 0
Other Launch Support Program | 80d | 2026-06-29 | 2026-10-16 | Issues |  | 0% |  |  |  |  | Issues | TRUE |  | 182108 | 0
X-566 Launch Support Project | 60d | 2026-06-29 | 2026-09-18 |  | 49 | 0% |  | RE-1 Team | [5 empty] | 85046 | 0
K-45 Launch Support Project | 60d | 2026-07-27 | 2026-10-16 |  | 52SS +20d | 0% |  | RE-2 Team | [5 empty] | 97062 | 0
On Orbit Support Program | 500d | 2026-08-10 | 2028-07-07 | On Track |  | 0% |  |  |  | TRUE | On Track | TRUE |  | 349126 | 0
AF Missions Support Projects | 100d | 2027-05-03 | 2027-09-17 |  | 22FF +10d | 0% |  | COMM Team | [5 empty] | 70835 | 0
NASA Missions Support Projects | 100d | 2026-08-10 | 2026-12-25 |  | 38 | 0% |  | DS-1 Team | [5 empty] | 120085 | 0
Other Missions Support Projects | 100d | 2028-02-21 | 2028-07-07 |  | 43 | 0% |  | DS-2 Team | [5 empty] | 158206 | 0
Logistical Support Programs | 620d | 2024-08-12 | 2026-12-25 |  |  | 68% | [5 empty] | TRUE |  | 1222993 | 840862.04
Supplier Improvement Program | 460d | 2024-09-09 | 2026-06-12 | Blocked |  | 92% |  |  |  | TRUE | Blocked | TRUE |  | 297140 | 278755.3
Phase I Supplier Improvement Program Projects | 400d | 2024-09-09 | 2026-03-20 |  | 3SS +20d | 99% |  | LOG Team | [5 empty] | 187045 | 185174.55
Phase 2 Supplier Improvement Program Projects | 400d | 2024-12-02 | 2026-06-12 |  | 60SS +60d | 85% |  | LOG Team | [5 empty] | 110095 | 93580.75
Spare Parts Improvement Program | 340d | 2025-06-16 | 2026-10-02 | Issues |  | 60% |  |  |  | TRUE | Issues | TRUE |  | 209904 | 122826.53
Spare Parts Improvement Analysis Projects | 300d | 2025-06-16 | 2026-08-07 |  | 60SS +200d | 66% |  | LOG Team | [5 empty] | 89057 | 58777.62
Spare Parts Improvement Implementation Projects | 300d | 2025-08-11 | 2026-10-02 |  | 63SS +40d | 53% |  | LOG Team | [5 empty] | 120847 | 64048.91
Transportation Program | 400d | 2025-04-07 | 2026-10-16 | Issues |  | 66% |  |  |  | TRUE | Issues | TRUE |  | 255036 | 169493.36
Satellite Transportation Enhancement Requirements Analysis and Planning Projects | 300d | 2025-04-07 | 2026-05-29 |  | 60SS +150d | 83% |  | LOG Team | [5 empty] | 130958 | 108695.14
Launch Vehicle Transportation Enhancement Requirements Analysis and Planning Projects | 300d | 2025-08-25 | 2026-10-16 |  | 66SS +100d | 49% |  | LOG Team | [5 empty] | 124078 | 60798.22
Facilities Improvement and Construction Program | 600d | 2024-09-09 | 2026-12-25 | Blocked |  | 55% |  |  |  | TRUE | Blocked | TRUE |  | 229339 | 108765.69
Satellite and Launch Vehicle Manufacturing Facilities Continuing Maintenance Projects | 600d | 2024-09-09 | 2026-12-25 |  | 3SS +20d | 66% |  | FAC Team | [5 empty] | 100254 | 66167.64
X-Programs Satellite Development and Manufacturing Facilities Construction Projects | 300d | 2025-11-03 | 2026-12-25 |  | 69SS +300d | 33% |  | FAC Team | [5 empty] | 129085 | 42598.05
IT Support Program | 600d | 2024-08-12 | 2026-11-27 | Issues |  | 67% |  |  |  | TRUE | Issues | TRUE |  | 95866 | 66025.56
IT Infrastructure Refresh Projects | 600d | 2024-08-12 | 2026-11-27 |  | 3SS | 70% |  | IT Team | [5 empty] | 86042 | 60229.4
Business Intelligence, CRM, and Future Infrastructure Requirements Projects | 200d | 2025-10-06 | 2026-07-10 |  | 72SS +300d | 59% |  | IT Team | [5 empty] | 9824 | 5796.16
Human Resources Program | 600d | 2024-08-12 | 2026-11-27 | On Track |  | 70% |  |  |  | TRUE | On Track | TRUE |  | 135708 | 94995.6
Personnel Training Requirements Development Projects | 600d | 2024-08-12 | 2026-11-27 |  | 3SS | 70% |  | HR Team | [5 empty] | 135708 | 94995.6