## RFP Response and Award Timeline
Task Name | Duration | Start | Finish | OnePager | Predecessors | Assigned To | Allocation % | % Complete | Status | Comments
Initial RFP | 330d | 2024-01-31 | 2025-05-06
Contractor A RFP Response | 53d | 2024-01-31 | 2024-04-12 | TRUE |  | Contractor A
Contractors B&C Respond | 53d | 2024-01-31 | 2024-04-12 | TRUE |  | Contractor B
Requirements Revised | 1d | 2024-09-01 | 2024-09-01 | TRUE |  | Government
Contractor A Resubmission | 90d | 2024-09-02 | 2025-01-03 | TRUE |  | Contractor A
Contractors B&C Resubmit | 90d | 2024-09-02 | 2025-01-03 | TRUE |  | Contractor B
RFP Award to Contractor A | 1d | 2025-02-15 | 2025-02-15 | TRUE |  | Government
Contractors B&C Protest | 58d | 2025-02-15 | 2025-05-06 | TRUE |  | Contractor A
Recompetition | 33d | 2025-09-10 | 2025-10-25
Revised RFP Provided | 1d | 2025-09-10 | 2025-09-10 | TRUE |  | Government
Cancellation of RFP | 1d | 2025-10-25 | 2025-10-25 | TRUE |  | Government
New RFP | 392d | 2026-08-26 | 2028-02-24
Draft RFP Issued | 1d | 2026-08-26 | 2026-08-26 | TRUE |  | Government
Revised RFP Released | 1d | 2027-02-23 | 2027-02-23 | TRUE |  | Government
Contractor A Draft RFP Response | 130d | 2026-08-26 | 2027-02-23 | TRUE |  | Contractor A
Revisions | 97d | 2027-02-25 | 2027-07-09 | TRUE |  | Contractor A
Contractors B&C Draft RFP Response | 130d | 2026-08-26 | 2027-02-23 | TRUE |  | Contractor B
Contractor B Withdraws | 1d | 2027-03-08 | 2027-03-08 | TRUE |  | Contractor B
Con. C Response | 59d | 2027-04-20 | 2027-07-09 | TRUE |  | Contractor C
Contractor D Response | 1d | 2027-07-01 | 2027-07-01 | TRUE |  | Contractor D
Contractor D Bid Rejection | 1d | 2027-07-01 | 2027-07-01 | TRUE |  | Government
Contractor D Protest | 48d | 2027-08-01 | 2027-10-05 | TRUE |  | Contractor D
Contractor A Final Bid Submission | 155d | 2027-07-09 | 2028-02-10 | TRUE |  | Contractor A
Contractor C Final Bid Submission | 155d | 2027-07-09 | 2028-02-10 | TRUE |  | Contractor C
Final Award to Contractor C | 1d | 2028-02-24 | 2028-02-24 | TRUE |  | Government