## Sheet1
ID | Task Name | Start Date | Finish Date | Actor | Phase
1 | Contractor A RFP Response | 2024-01-31 | 2024-04-12 | Contractor A | Initial RFP
2 | Contractors B&C Respond | 2024-01-31 | 2024-04-12 | Contractor B | Initial RFP
3 | Requirements Revised | 2024-09-01 | 2024-09-01 | Government | Initial RFP
4 | Contractor A Resubmission | 2024-09-02 | 2025-01-03 | Contractor A | Initial RFP
5 | Contractors B&C Resubmit | 2024-09-02 | 2025-01-03 | Contractor B | Initial RFP
6 | RFP Award to Contractor A | 2025-02-15 | 2025-02-15 | Government | Initial RFP
7 | Contractors B&C Protest | 2025-02-15 | 2025-05-06 | Contractor A | Initial RFP
8 | Revised RFP Provided | 2025-09-10 | 2025-09-10 | Government | Recompetition
9 | Cancellation of RFP | 2025-10-25 | 2025-10-25 | Government | Recompetition
10 | Draft RFP Issued | 2026-08-26 | 2026-08-26 | Government | New RFP
11 | Revised RFP Released | 2027-02-23 | 2027-02-23 | Government | New RFP
12 | Contractor A Draft RFP Response | 2026-08-26 | 2027-02-23 | Contractor A | New RFP
13 | Revisions | 2027-02-25 | 2027-07-09 | Contractor A | New RFP
14 | Contractors B&C Draft RFP Response | 2026-08-26 | 2027-02-23 | Contractor B | New RFP
15 | Contractor B Withdraws | 2027-03-08 | 2027-03-08 | Contractor B | New RFP
16 | Con. C Response | 2027-04-20 | 2027-07-09 | Contractor C | New RFP
17 | Contractor D Response | 2027-07-01 | 2027-07-01 | Contractor D | New RFP
18 | Contractor D Bid Rejection | 2027-07-01 | 2027-07-01 | Government | New RFP
19 | Contractor D Protest | 2027-08-01 | 2027-10-05 | Contractor D | New RFP
20 | Contractor A Final Bid Submission | 2027-07-09 | 2028-02-10 | Contractor A | New RFP
21 | Contractor C Final Bid Submission | 2027-07-09 | 2028-02-10 | Contractor C | New RFP
22 | Final Award to Contractor C | 2028-02-24 | 2028-02-24 | Government | New RFP