## Task_Table
ID | Name | Start | Finish | Baseline Start | Baseline Finish | % Completed | Predecessors | Phase | Show It | Resource
1 | Cosmic Galaxy Consulting Services-Engagement Schedule | 2019-05-06 | 2019-09-03 | 2019-05-06 | 2019-09-03 | 35% |  |  | No
2 | Sales Process | 2019-05-06 | 2019-06-18 | 2019-05-06 | 2019-06-18 | 100% |  | Sales Process | No
3 | Refine Requirements with Customer | 2019-05-06 | 2019-05-31 | 2019-05-06 | 2019-05-31 | 100% |  | Sales Process | Yes | Sales Executive
4 | Draft and Finalize Statement of Work | 2019-06-03 | 2019-06-07 | 2019-06-03 | 2019-06-07 | 100% |  | Sales Process | Yes | Sales Executive
5 | Negotiate Contract Terms and Conditions, Rates, and Schedule | 2019-06-03 | 2019-06-14 | 2019-06-03 | 2019-06-14 | 100% |  | Sales Process | Yes | Practice Director
6 | Sign Contract | 2019-06-10 | 2019-06-14 | 2019-06-10 | 2019-06-14 | 100% |  | Sales Process | Yes | Practice Director
7 | Kick-Off | 2019-06-17 | 2019-06-19 | 2019-06-17 | 2019-06-19 | 0% |  | Kick-Off | No
8 | Plan and Conduct Kick-Off Meeting with Engagement Team and Customer | 2019-06-17 | 2019-06-17 | 2019-06-17 | 2019-06-17 | 0% |  | Kick-Off | Yes | Engagement Manager
9 | Finalize Engagement Schedule, Access to Resources, and Reporting Scenario | 2019-06-17 | 2019-06-17 | 2019-06-17 | 2019-06-17 | 0% |  | Kick-Off | Yes | Engagement Manager
10 | Engagement | 2019-06-21 | 2019-08-22 | 2019-06-21 | 2019-08-22 | 0% |  | Engagement | No
11 | Conduct Preliminary Interviews | 2019-06-21 | 2019-07-04 | 2019-06-15 | 2019-07-04 | 0% |  | Engagement | Yes | Associate Consultants
12 | Conduct Follow Up Interviews | 2019-07-03 | 2019-07-09 | 2019-07-03 | 2019-07-09 | 0% |  | Engagement | Yes | Associate Consultants
13 | Develop Preliminary Findings | 2019-07-05 | 2019-07-18 | 2019-07-04 | 2019-07-20 | 0% |  | Engagement | Yes | Associate Consultants
14 | Coordinate Preliminary Findings with Customer | 2019-07-19 | 2019-07-25 | 2019-07-19 | 2019-07-25 | 0% |  | Engagement | Yes | Engagement Manager
15 | Conduct Follow Up Research, Interviews, Data Analysis | 2019-07-26 | 2019-08-08 | 2019-07-26 | 2019-08-08 | 0% |  | Engagement | Yes | Associate Consultants
16 | Formulate Preliminary Recommendations and Rationale | 2019-07-24 | 2019-08-13 | 2019-07-20 | 2019-08-13 | 0% |  | Engagement | Yes | Associate Consultants
17 | Coordinate Preliminary Recommendations and Rationale with Customer | 2019-08-12 | 2019-08-16 | 2019-08-12 | 2019-08-16 | 0% |  | Engagement | Yes | Associate Consultants
18 | Make Adjustments to Recommendations, Rationale, and Prepare Final Report | 2019-08-16 | 2019-08-22 | 2019-08-10 | 2019-08-20 | 0% |  | Engagement | Yes | Engagement Manager
19 | Closeout | 2019-08-23 | 2019-09-03 | 2019-08-23 | 2019-09-03 | 0% |  | Closeout | No
20 | Present Final Report to Customer | 2019-08-23 | 2019-08-26 | 2019-08-23 | 2019-08-26 | 0% |  | Closeout | Yes | Engagement Manager
21 | Conduct any Follow Up Activity | 2019-08-27 | 2019-09-02 | 2019-08-22 | 2019-09-01 | 0% |  | Closeout | Yes | Engagement Manager
22 | Deliver Final Documented Reports | 2019-09-03 | 2019-09-03 | 2019-09-03 | 2019-09-03 | 0% |  | Closeout | Yes | Engagement Manager
23 | Engagement Complete | 2019-09-03 | 2019-09-03 | 2019-09-03 | 2019-09-03 | 0% |  | Closeout | Yes | Engagement Manager
24 | Engagement Management | 2019-07-08 | 2019-09-02 | 2019-07-08 | 2019-09-02 | 0% |  | Engagement Management | No
25 | First Status Report | 2019-07-09 | 2019-07-09 | 2019-07-09 | 2019-07-09 | 0% | 12 | Engagement Management | Yes | Engagement Manager
26 | Second Status Report | 2019-08-08 | 2019-08-08 | 2019-08-08 | 2019-08-08 | 0% | 16 | Engagement Management | Yes | Engagement Manager
27 | Final Status Report | 2019-09-03 | 2019-09-03 | 2019-09-03 | 2019-09-03 | 0% | 23 | Engagement Management | Yes | Engagement Manager