## Process Improvement Project Sch
OnePager | Task Name | Duration | Start Date | End Date | Predecessors | % Complete | Status | Assigned To | Comments | Start | Finish
TRUE | Proposal | 50d | 2021-01-04 | 2021-03-12 |  | 100% |  | Sales Team
| Review and Respond to Request for Proposal | 20d | 2021-01-04 | 2021-01-29 |  | 100% |  | Sales Team
| Conduct Discussions with Prospective Client | 20d | 2021-02-01 | 2021-02-26 | 2 | 100% |  | Sales Team
| Negotiate Contract, Schedule, Deliverables, and Success Measures | 10d | 2021-03-01 | 2021-03-12 | 3 | 100% |  | Sales Team
TRUE | Initial Entrance | 7d | 2021-03-15 | 2021-03-23 |  | 100% |  | Sales Team
| Conduct Kick-Off Meeting | 1d | 2021-03-15 | 2021-03-15 | 4 | 100% |  | Sales Team
| Schedule and Conduct Orientation Meeting with Employees, Managers, and Staff | 5d | 2021-03-16 | 2021-03-22 | 6 | 100% |  | Sales Team
| Formulate and Publish Goals and Objectives of Process Improvement Project | 1d | 2021-03-23 | 2021-03-23 | 7 | 100% |  | Sales Team
TRUE | Research | 115d | 2021-03-24 | 2021-08-31 |  | 43% |  | Analysis Team
| Baselining | 20d | 2021-03-24 | 2021-04-20 |  | 100%
TRUE | Baseline Current Processes and Procedures | 20d | 2021-03-24 | 2021-04-20 | 8 | 100% |  | Analysis Team
| PIP 1 | 25d | 2021-04-21 | 2021-05-25 |  | 100%
TRUE | First Process Improvement Presentation | 5d | 2021-04-21 | 2021-04-27 | 11 | 100% |  | Analysis Team
TRUE | First Process Improvement Buy-In Meetings | 20d | 2021-04-28 | 2021-05-25 | 13 | 100% |  | Analysis Team
| PIP 2 | 25d | 2021-05-12 | 2021-06-15 |  | 52%
TRUE | Second Process Improvement Presentation | 5d | 2021-05-12 | 2021-05-18 | 14SS +10d | 100% |  | Analysis Team
TRUE | Second Process Improvement Buy-In Meetings | 20d | 2021-05-19 | 2021-06-15 | 16 | 40% |  | Analysis Team
| PIP 3 | 25d | 2021-06-02 | 2021-07-06 |  | 0%
TRUE | Third Process Improvement Presentation | 5d | 2021-06-02 | 2021-06-08 | 17SS +10d | 0% |  | Analysis Team
TRUE | Third Process Improvement Buy-In Meetings | 20d | 2021-06-09 | 2021-07-06 | 19 | 0% |  | Analysis Team
| Implementation Planning | 30d | 2021-07-07 | 2021-08-17 |  | 0%
TRUE | Implementation Plan and Schedule | 10d | 2021-07-07 | 2021-07-20 | 20 | 0% |  | Analysis Team
TRUE | Implementation Plan Buy-In Meeting | 20d | 2021-07-21 | 2021-08-17 | 22 | 0% |  | Analysis Team
| Signoff | 10d | 2021-08-18 | 2021-08-31 |  | 0%
TRUE | Attain Buy-In to Process Improvement Plan | 10d | 2021-08-18 | 2021-08-31 | 23 | 0% |  | Analysis Team
TRUE | Implementation | 125d | 2021-09-01 | 2022-02-22 |  | 0% |  | Delivery Team
| Execute Process Improvement Plan Actions | 120d | 2021-09-01 | 2022-02-15 | 25 | 0% |  | Delivery Team
| Conduct Status Assessment I | 5d | 2021-10-27 | 2021-11-02 | 27SS +40d | 0% |  | Delivery Team
| Conduct Status Assessment II | 5d | 2021-12-22 | 2021-12-28 | 28SS +40d | 0% |  | Delivery Team
| Conduct Status Assessment III | 5d | 2022-02-16 | 2022-02-22 | 29SS +40d | 0% |  | Delivery Team
| Complete | 0 | 2022-02-22 | 2022-02-22 | 28, 29, 30 | 0%