## Midstream Project Portfolio
Task Name | Duration | Start Date | End Date | Production Target | Predecessors | % Complete | OnePager | Status | Assigned To | Comments | Start | Finish | Flag20
Project A | 1522d | 2016-06-01 | 2022-03-31 |  |  | 29%
Marcellus Shale | 1522d | 2016-06-01 | 2022-03-31 |  |  | 33%
Acquisition | 90d | 2016-06-01 | 2016-10-04 |  |  | 100% | TRUE | [5 empty] | TRUE
Closing | 1d | 2016-10-05 | 2016-10-05 |  | 3 | 100% | TRUE | [5 empty] | TRUE
Design | 180d | 2016-10-06 | 2017-06-14 |  | 4 | 100% | TRUE | [5 empty] | TRUE
Regulatory Review | 90d | 2017-06-15 | 2017-10-18 |  | 5 | 100% | TRUE | [5 empty] | TRUE
Construction | 365d | 2017-10-19 | 2019-03-13 |  | 6 | 38% | TRUE | [5 empty] | TRUE
Regulatory Review | 30d | 2019-03-14 | 2019-04-24 |  | 7 | 0% | TRUE | [5 empty] | TRUE
Go-Live Preparation | 30d | 2019-04-25 | 2019-06-05 |  | 8 | 0% | TRUE | [5 empty] | TRUE
Launch | 736d | 2019-06-06 | 2022-03-31 | 998000 | 9 | 0% | TRUE | [5 empty] | TRUE
Newark East | 1404d | 2016-11-14 | 2022-03-31 |  |  | 27%
Acquisition | 90d | 2016-11-14 | 2017-03-17 |  |  | 100% | TRUE | [5 empty] | TRUE
Closing | 1d | 2017-03-20 | 2017-03-20 |  | 12 | 100% | TRUE | [5 empty] | TRUE
Design | 120d | 2017-03-21 | 2017-09-04 |  | 13 | 100% | TRUE | [5 empty] | TRUE
Regulatory Review | 90d | 2017-09-05 | 2018-01-08 |  | 14 | 100% | TRUE | [5 empty] | TRUE
Construction | 500d | 2018-01-09 | 2019-12-09 |  | 15 | 16% | TRUE | [5 empty] | TRUE
Regulatory Review | 30d | 2019-12-10 | 2020-01-20 |  | 16 | 0% | TRUE | [5 empty] | TRUE
Go-Live Preparation | 30d | 2020-01-21 | 2020-03-02 |  | 17 | 0% | TRUE | [5 empty] | TRUE
Launch | 543d | 2020-03-03 | 2022-03-31 | 803000 | 18 | 0% | TRUE | [5 empty] | TRUE
B-43 Area | 1404d | 2016-11-14 | 2022-03-31 |  |  | 27%
Acquisition | 120d | 2016-11-14 | 2017-04-28 |  |  | 100% | TRUE | [5 empty] | TRUE
Closing | 1d | 2017-05-01 | 2017-05-01 |  | 21 | 100% | TRUE | [5 empty] | TRUE
Design | 180d | 2017-05-02 | 2018-01-08 |  | 22 | 100% | TRUE | [5 empty] | TRUE
Regulatory Review | 90d | 2018-01-09 | 2018-05-14 |  | 23 | 89% | TRUE | [5 empty] | TRUE
Construction | 490d | 2018-05-15 | 2020-03-30 |  | 24 | 0% | TRUE | [5 empty] | TRUE
Regulatory Review | 30d | 2020-03-31 | 2020-05-11 |  | 25 | 0% | TRUE | [5 empty] | TRUE
Go-Live Preparation | 30d | 2020-05-12 | 2020-06-22 |  | 26 | 0% | TRUE | [5 empty] | TRUE
Launch | 463d | 2020-06-23 | 2022-03-31 | 723000 | 27 | 0% | TRUE | [5 empty] | TRUE
San Juan Basin | 1404d | 2016-11-14 | 2022-03-31 |  |  | 27%
Acquisition | 180d | 2016-11-14 | 2017-07-21 |  |  | 100% | TRUE | [5 empty] | TRUE
Closing | 1d | 2017-07-24 | 2017-07-24 |  | 30 | 100% | TRUE | [5 empty] | TRUE
Design | 180d | 2017-07-25 | 2018-04-02 |  | 31 | 100% | TRUE | [5 empty] | TRUE
Regulatory Review | 90d | 2018-04-03 | 2018-08-06 |  | 32 | 22% | TRUE | [5 empty] | TRUE
Construction | 800d | 2018-08-07 | 2021-08-30 |  | 33 | 0% | TRUE | [5 empty] | TRUE
Regulatory Review | 30d | 2021-08-31 | 2021-10-11 |  | 34 | 0% | TRUE | [5 empty] | TRUE
Go-Live Preparation | 30d | 2021-10-12 | 2021-11-22 |  | 35 | 0% | TRUE | [5 empty] | TRUE
Launch | 93d | 2021-11-23 | 2022-03-31 | 353000 | 36 | 0% | TRUE | [5 empty] | TRUE
Project B | 1404d | 2016-11-14 | 2022-03-31 |  |  | 23%
Haynesville Shale | 1404d | 2016-11-14 | 2022-03-31 |  |  | 27%
Acquisition | 30d | 2016-11-14 | 2016-12-23 |  |  | 100% | TRUE | [5 empty] | TRUE
Closing | 1d | 2016-12-26 | 2016-12-26 |  | 40 | 100% | TRUE | [5 empty] | TRUE
Design | 200d | 2016-12-27 | 2017-10-02 |  | 41 | 100% | TRUE | [5 empty] | TRUE
Regulatory Review | 90d | 2017-10-03 | 2018-02-05 |  | 42 | 100% | TRUE | [5 empty] | TRUE
Construction | 300d | 2018-02-06 | 2019-04-01 |  | 43 | 20% | TRUE | [5 empty] | TRUE
Regulatory Review | 60d | 2019-04-02 | 2019-06-24 |  | 44 | 0% | TRUE | [5 empty] | TRUE
Go-Live Preparation | 30d | 2019-06-25 | 2019-08-05 |  | 45 | 0% | TRUE | [5 empty] | TRUE
Launch | 693d | 2019-08-06 | 2022-03-31 | 953000 | 46 | 0% | TRUE | [5 empty] | TRUE
Pinedale | 1404d | 2016-11-14 | 2022-03-31 |  |  | 27%
Acquisition | 60d | 2016-11-14 | 2017-02-03 |  |  | 100% | TRUE | [5 empty] | TRUE
Closing | 1d | 2017-02-06 | 2017-02-06 |  | 49 | 100% | TRUE | [5 empty] | TRUE
Design | 180d | 2017-02-07 | 2017-10-16 |  | 50 | 100% | TRUE | [5 empty] | TRUE
Regulatory Review | 90d | 2017-10-17 | 2018-02-19 |  | 51 | 100% | TRUE | [5 empty] | TRUE
Construction | 750d | 2018-02-20 | 2021-01-04 |  | 52 | 7% | TRUE | [5 empty] | TRUE
Regulatory Review | 30d | 2021-01-05 | 2021-02-15 |  | 53 | 0% | TRUE | [5 empty] | TRUE
Go-Live Preparation | 30d | 2021-02-16 | 2021-03-29 |  | 54 | 0% | TRUE | [5 empty] | TRUE
Launch | 263d | 2021-03-30 | 2022-03-31 | 523000 | 55 | 0% | TRUE | [5 empty] | TRUE
Carthage | 1205d | 2017-08-18 | 2022-03-31 |  |  | 15%
Acquisition | 90d | 2017-08-18 | 2017-12-21 |  |  | 100% | TRUE | [5 empty] | TRUE
Closing | 1d | 2017-12-22 | 2017-12-22 |  | 58 | 100% | TRUE | [5 empty] | TRUE
Design | 180d | 2017-12-25 | 2018-08-31 |  | 59 | 51% | TRUE | [5 empty] | TRUE
Regulatory Review | 90d | 2018-09-03 | 2019-01-04 |  | 60 | 0% | TRUE | [5 empty] | TRUE
Construction | 400d | 2019-01-07 | 2020-07-17 |  | 61 | 0% | TRUE | [5 empty] | TRUE
Regulatory Review | 30d | 2020-07-20 | 2020-08-28 |  | 62 | 0% | TRUE | [5 empty] | TRUE
Go-Live Preparation | 30d | 2020-08-31 | 2020-10-09 |  | 63 | 0% | TRUE | [5 empty] | TRUE
Launch | 384d | 2020-10-12 | 2022-03-31 | 644000 | 64 | 0% | TRUE | [5 empty] | TRUE
Project C | 1404d | 2016-11-14 | 2022-03-31 |  |  | 23%
Jonah | 1404d | 2016-11-14 | 2022-03-31 |  |  | 27%
Acquisition | 90d | 2016-11-14 | 2017-03-17 |  |  | 100% | TRUE | [5 empty] | TRUE
Closing | 1d | 2017-03-20 | 2017-03-20 |  | 68 | 100% | TRUE | [5 empty] | TRUE
Design | 180d | 2017-03-21 | 2017-11-27 |  | 69 | 100% | TRUE | [5 empty] | TRUE
Regulatory Review | 90d | 2017-11-28 | 2018-04-02 |  | 70 | 100% | TRUE | [5 empty] | TRUE
Construction | 620d | 2018-04-03 | 2020-08-17 |  | 71 | 3% | TRUE | [5 empty] | TRUE
Regulatory Review | 30d | 2020-08-18 | 2020-09-28 |  | 72 | 0% | TRUE | [5 empty] | TRUE
Go-Live Preparation | 30d | 2020-09-29 | 2020-11-09 |  | 73 | 0% | TRUE | [5 empty] | TRUE
Launch | 363d | 2020-11-10 | 2022-03-31 | 623000 | 74 | 0% | TRUE | [5 empty] | TRUE
Wattenberg | 1176d | 2017-09-28 | 2022-03-31 |  |  | 13%
Acquisition | 75d | 2017-09-28 | 2018-01-10 |  |  | 100% | TRUE | [5 empty] | TRUE
Closing | 1d | 2018-01-11 | 2018-01-11 |  | 77 | 100% | TRUE | [5 empty] | TRUE
Design | 180d | 2018-01-12 | 2018-09-20 |  | 78 | 43% | TRUE | [5 empty] | TRUE
Regulatory Review | 90d | 2018-09-21 | 2019-01-24 |  | 79 | 0% | TRUE | [5 empty] | TRUE
Construction | 400d | 2019-01-25 | 2020-08-06 |  | 80 | 0% | TRUE | [5 empty] | TRUE
Regulatory Review | 30d | 2020-08-07 | 2020-09-17 |  | 81 | 0% | TRUE | [5 empty] | TRUE
Go-Live Preparation | 30d | 2020-09-18 | 2020-10-29 |  | 82 | 0% | TRUE | [5 empty] | TRUE
Launch | 370d | 2020-10-30 | 2022-03-31 | 632000 | 83 | 0% | TRUE | [5 empty] | TRUE
Prudhoe Bay | 1404d | 2016-11-14 | 2022-03-31 |  |  | 27%
Acquisition | 80d | 2016-11-14 | 2017-03-03 |  |  | 100% | TRUE | [5 empty] | TRUE
Closing | 1d | 2017-03-06 | 2017-03-06 |  | 86 | 100% | TRUE | [5 empty] | TRUE
Design | 90d | 2017-03-07 | 2017-07-10 |  | 87 | 100% | TRUE | [5 empty] | TRUE
Regulatory Review | 90d | 2017-07-11 | 2017-11-13 |  | 88 | 100% | TRUE | [5 empty] | TRUE
Construction | 400d | 2017-11-14 | 2019-05-27 |  | 89 | 30% | TRUE | [5 empty] | TRUE
Regulatory Review | 30d | 2019-05-28 | 2019-07-08 |  | 90 | 0% | TRUE | [5 empty] | TRUE
Go-Live Preparation | 30d | 2019-07-09 | 2019-08-19 |  | 91 | 0% | TRUE | [5 empty] | TRUE
Launch | 683d | 2019-08-20 | 2022-03-31 | 292000 | 92 | 0% | TRUE | [5 empty] | TRUE