## Task_Table
ID | Name | Project | Site | Duration | Start | Finish | Production Target
1 | Acquisition | Project A | Marcellus Shale | 90 days | 2016-06-01 08:00 | 2016-10-04 17:00
2 | Closing | Project A | Marcellus Shale | 1 day | 2016-10-05 08:00 | 2016-10-05 17:00
3 | Design | Project A | Marcellus Shale | 180 days | 2016-10-06 08:00 | 2017-06-14 17:00
4 | Regulatory Review | Project A | Marcellus Shale | 90 days | 2017-06-15 08:00 | 2017-10-18 17:00
5 | Construction | Project A | Marcellus Shale | 365 days | 2017-10-19 08:00 | 2019-03-13 17:00
6 | Regulatory Review | Project A | Marcellus Shale | 30 days | 2019-03-14 08:00 | 2019-04-24 17:00
7 | Go-Live Preparation | Project A | Marcellus Shale | 30 days | 2019-04-25 08:00 | 2019-06-05 17:00
8 | Launch | Project A | Marcellus Shale | 90 days | 2019-06-06 08:00 | 2022-03-31 | 998000
9 | Acquisition | Project A | Newark East | 90 days | 2016-11-14 08:00 | 2017-03-17 17:00
10 | Closing | Project A | Newark East | 1 day | 2017-03-20 08:00 | 2017-03-20 17:00
11 | Design | Project A | Newark East | 120 days | 2017-03-21 08:00 | 2017-09-04 17:00
12 | Regulatory Review | Project A | Newark East | 90 days | 2017-09-05 08:00 | 2018-01-08 17:00
13 | Construction | Project A | Newark East | 500 days | 2018-01-09 08:00 | 2019-12-09 17:00
14 | Regulatory Review | Project A | Newark East | 30 days | 2019-12-10 08:00 | 2020-01-20 17:00
15 | Go-Live Preparation | Project A | Newark East | 30 days | 2020-01-21 08:00 | 2020-03-02 17:00
16 | Launch | Project A | Newark East | 90 days | 2020-03-03 08:00 | 2022-03-31 | 803000
17 | Acquisition | Project A | B-43 Area | 120 days | 2016-11-14 08:00 | 2017-04-28 17:00
18 | Closing | Project A | B-43 Area | 1 day | 2017-05-01 08:00 | 2017-05-01 17:00
19 | Design | Project A | B-43 Area | 180 days | 2017-05-02 08:00 | 2018-01-08 17:00
20 | Regulatory Review | Project A | B-43 Area | 90 days | 2018-01-09 08:00 | 2018-05-14 17:00
21 | Construction | Project A | B-43 Area | 490 days | 2018-05-15 08:00 | 2020-03-30 17:00
22 | Regulatory Review | Project A | B-43 Area | 30 days | 2020-03-31 08:00 | 2020-05-11 17:00
23 | Go-Live Preparation | Project A | B-43 Area | 30 days | 2020-05-12 08:00 | 2020-06-22 17:00
24 | Launch | Project A | B-43 Area | 90 days | 2020-06-23 08:00 | 2022-03-31 | 723000
25 | Acquisition | Project A | San Juan Basin | 180 days | 2016-11-14 08:00 | 2017-07-21 17:00
26 | Closing | Project A | San Juan Basin | 1 day | 2017-07-24 08:00 | 2017-07-24 17:00
27 | Design | Project A | San Juan Basin | 180 days | 2017-07-25 08:00 | 2018-04-02 17:00
28 | Regulatory Review | Project A | San Juan Basin | 90 days | 2018-04-03 08:00 | 2018-08-06 17:00
29 | Construction | Project A | San Juan Basin | 800 days | 2018-08-07 08:00 | 2021-08-30 17:00
30 | Regulatory Review | Project A | San Juan Basin | 30 days | 2021-08-31 08:00 | 2021-10-11 17:00
31 | Go-Live Preparation | Project A | San Juan Basin | 30 days | 2021-10-12 08:00 | 2021-11-22 17:00
32 | Launch | Project A | San Juan Basin | 90 days | 2021-11-23 08:00 | 2022-03-31 | 353000
33 | Acquisition | Project B | Haynesville Shale | 30 days | 2016-11-14 08:00 | 2016-12-23 17:00
34 | Closing | Project B | Haynesville Shale | 1 day | 2016-12-26 08:00 | 2016-12-26 17:00
35 | Design | Project B | Haynesville Shale | 200 days | 2016-12-27 08:00 | 2017-10-02 17:00
36 | Regulatory Review | Project B | Haynesville Shale | 90 days | 2017-10-03 08:00 | 2018-02-05 17:00
37 | Construction | Project B | Haynesville Shale | 300 days | 2018-02-06 08:00 | 2019-04-01 17:00
38 | Regulatory Review | Project B | Haynesville Shale | 60 days | 2019-04-02 08:00 | 2019-06-24 17:00
39 | Go-Live Preparation | Project B | Haynesville Shale | 30 days | 2019-06-25 08:00 | 2019-08-05 17:00
40 | Launch | Project B | Haynesville Shale | 90 days | 2019-08-06 08:00 | 2022-03-31 | 953000
41 | Acquisition | Project B | Pinedale | 60 days | 2016-11-14 08:00 | 2017-02-03 17:00
42 | Closing | Project B | Pinedale | 1 day | 2017-02-06 08:00 | 2017-02-06 17:00
43 | Design | Project B | Pinedale | 180 days | 2017-02-07 08:00 | 2017-10-16 17:00
44 | Regulatory Review | Project B | Pinedale | 90 days | 2017-10-17 08:00 | 2018-02-19 17:00
45 | Construction | Project B | Pinedale | 750 days | 2018-02-20 08:00 | 2021-01-04 17:00
46 | Regulatory Review | Project B | Pinedale | 30 days | 2021-01-05 08:00 | 2021-02-15 17:00
47 | Go-Live Preparation | Project B | Pinedale | 30 days | 2021-02-16 08:00 | 2021-03-29 17:00
48 | Launch | Project B | Pinedale | 90 days | 2021-03-30 08:00 | 2022-03-31 | 523000
49 | Acquisition | Project B | Carthage | 90 days | 2017-08-18 08:00 | 2017-12-21 17:00
50 | Closing | Project B | Carthage | 1 day | 2017-12-22 08:00 | 2017-12-22 17:00
51 | Design | Project B | Carthage | 180 days | 2017-12-25 08:00 | 2018-08-31 17:00
52 | Regulatory Review | Project B | Carthage | 90 days | 2018-09-03 08:00 | 2019-01-04 17:00
53 | Construction | Project B | Carthage | 400 days | 2019-01-07 08:00 | 2020-07-17 17:00
54 | Regulatory Review | Project B | Carthage | 30 days | 2020-07-20 08:00 | 2020-08-28 17:00
55 | Go-Live Preparation | Project B | Carthage | 30 days | 2020-08-31 08:00 | 2020-10-09 17:00
56 | Launch | Project B | Carthage | 90 days | 2020-10-12 08:00 | 2022-03-31 | 644000
57 | Acquisition | Project C | Jonah | 90 days | 2016-11-14 08:00 | 2017-03-17 17:00
58 | Closing | Project C | Jonah | 1 day | 2017-03-20 08:00 | 2017-03-20 17:00
59 | Design | Project C | Jonah | 180 days | 2017-03-21 08:00 | 2017-11-27 17:00
60 | Regulatory Review | Project C | Jonah | 90 days | 2017-11-28 08:00 | 2018-04-02 17:00
61 | Construction | Project C | Jonah | 620 days | 2018-04-03 08:00 | 2020-08-17 17:00
62 | Regulatory Review | Project C | Jonah | 30 days | 2020-08-18 08:00 | 2020-09-28 17:00
63 | Go-Live Preparation | Project C | Jonah | 30 days | 2020-09-29 08:00 | 2020-11-09 17:00
64 | Launch | Project C | Jonah | 90 days | 2020-11-10 08:00 | 2022-03-31 | 623000
65 | Acquisition | Project C | Wattenberg | 75 days | 2017-09-28 08:00 | 2018-01-10 17:00
66 | Closing | Project C | Wattenberg | 1 day | 2018-01-11 08:00 | 2018-01-11 17:00
67 | Design | Project C | Wattenberg | 180 days | 2018-01-12 08:00 | 2018-09-20 17:00
68 | Regulatory Review | Project C | Wattenberg | 90 days | 2018-09-21 08:00 | 2019-01-24 17:00
69 | Construction | Project C | Wattenberg | 400 days | 2019-01-25 08:00 | 2020-08-06 17:00
70 | Regulatory Review | Project C | Wattenberg | 30 days | 2020-08-07 08:00 | 2020-09-17 17:00
71 | Go-Live Preparation | Project C | Wattenberg | 30 days | 2020-09-18 08:00 | 2020-10-29 17:00
72 | Launch | Project C | Wattenberg | 90 days | 2020-10-30 08:00 | 2022-03-31 | 632000
73 | Acquisition | Project C | Prudhoe Bay | 80 days | 2016-11-14 08:00 | 2017-03-03 17:00
74 | Closing | Project C | Prudhoe Bay | 1 day | 2017-03-06 08:00 | 2017-03-06 17:00
75 | Design | Project C | Prudhoe Bay | 90 days | 2017-03-07 08:00 | 2017-07-10 17:00
76 | Regulatory Review | Project C | Prudhoe Bay | 90 days | 2017-07-11 08:00 | 2017-11-13 17:00
77 | Construction | Project C | Prudhoe Bay | 400 days | 2017-11-14 08:00 | 2019-05-27 17:00
78 | Regulatory Review | Project C | Prudhoe Bay | 30 days | 2019-05-28 08:00 | 2019-07-08 17:00
79 | Go-Live Preparation | Project C | Prudhoe Bay | 30 days | 2019-07-09 08:00 | 2019-08-19 17:00
80 | Launch | Project C | Prudhoe Bay | 90 days | 2019-08-20 08:00 | 2022-03-31 | 292000