## Task_Table
ID | Name | Start | Finish | Predecessors | Show It | % Complete | Phases | Resource Names
1 | Cosmic Galaxy, Inc. Initial Public Offering (IPO) Project Plan | 2019-04-01 08:00 | 2020-04-17 17:00 |  | No | 24%
2 | Pre-Decision Planning | 2019-04-01 08:00 | 2019-06-10 17:00 |  | No | 99% | Pre-Planning
3 | Review Financial History and Funding Requirements Plans | 2019-04-01 08:00 | 2019-04-26 17:00 |  | Yes | 100% | Pre-Planning | Finance Dept
4 | Review other Operations, Marketing, Personnel, and Facilities Plans for Consistency | 2019-04-08 08:00 | 2019-05-03 17:00 |  | Yes | 100% | Pre-Planning | Senior Mgt
5 | Determine Funds Needs and Timeframe | 2019-04-22 08:00 | 2019-05-17 17:00 |  | Yes | 100% | Pre-Planning | Finance Dept
6 | Review and Coordinate with Senior Management | 2019-05-20 08:00 | 2019-05-24 17:00 |  | Yes | 100% | Pre-Planning | Senior Mgt
7 | Build Presentation for Board of Directors | 2019-05-27 08:00 | 2019-05-31 17:00 |  | Yes | 100% | Pre-Planning | Finance Dept
8 | Present to Board of Directors | 2019-06-03 08:00 | 2019-06-03 17:00 |  | Yes | 100% | Pre-Planning | Board of Directors
9 | Post Board of Director's Meeting Guidance Implementation | 2019-06-03 08:00 | 2019-06-07 17:00 |  | Yes | 100% | Pre-Planning | Senior Mgt
10 | Go/No Go Decision | 2019-06-10 08:00 | 2019-06-10 17:00 |  | Yes | 0% | Pre-Planning | Board of Directors
11 | IPO Project Plan | 2019-06-10 08:00 | 2019-08-09 17:00 |  | No | 9% | Detail-Planning
12 | Create Requirements Package for Financial Consultant | 2019-06-10 08:00 | 2019-07-05 17:00 | 10 | Yes | 20% | Detail-Planning | Finance Dept
13 | Select and Orient Financial Consultant | 2019-07-08 08:00 | 2019-07-26 17:00 |  | Yes | 0% | Detail-Planning | Purchasing Dept
14 | Create IPO Detailed Plan | 2019-07-29 08:00 | 2019-08-09 17:00 |  | Yes | 0% | Detail-Planning | Consultant
15 | Review Number 1 | 2019-08-09 08:00 | 2019-08-09 17:00 |  | Yes | 0% | Detail-Planning | Senior Mgt
16 | Local Commercial Source to Support IPO | 2019-08-12 08:00 | 2019-10-25 17:00 |  | No | 0% | Gather Support
17 | Investigate Commercial Sources | 2019-08-12 08:00 | 2019-09-06 17:00 | 15 | Yes | 0% | Gather Support | Consultant
18 | Conduct Interviews | 2019-09-09 08:00 | 2019-10-04 17:00 |  | Yes | 0% | Gather Support | Finance Dept
19 | Negotiate Contract, Conduct Kick Off Meeting | 2019-10-07 08:00 | 2019-10-18 17:00 |  | Yes | 0% | Gather Support | Senior Mgt
20 | Review Financial Preparations for Start of IPO | 2019-10-21 08:00 | 2019-10-25 17:00 |  | Yes | 0% | Gather Support | Senior Mgt
21 | Review Number 2 | 2019-10-25 08:00 | 2019-10-25 17:00 |  | Yes | 0% | Gather Support | Senior Mgt
22 | IPO Execution | 2019-10-28 08:00 | 2019-12-25 17:00 |  | No | 0% | Execution
23 | Filings | 2019-10-28 08:00 | 2019-11-22 17:00 | 21 | Yes | 0% | Execution | Consultant
24 | Regulatory Q&A | 2019-11-25 08:00 | 2019-12-20 17:00 |  | Yes | 0% | Execution | Government
25 | Obtain Approval to Proceed with IPO | 2019-12-20 08:00 | 2019-12-20 17:00 |  | Yes | 0% | Execution | Government
26 | Review Number 3 | 2019-12-23 08:00 | 2019-12-23 17:00 |  | Yes | 0% | Execution | Senior Mgt
27 | Promotional Materials | 2019-11-04 08:00 | 2019-12-13 17:00 |  | Yes | 0% | Execution | Consultant
28 | Media Presentations | 2019-12-24 08:00 | 2019-12-25 17:00 |  | Yes | 0% | Execution | Consultant
29 | IPO Start Date | 2019-12-25 08:00 | 2019-12-25 17:00 |  | Yes | 0% | Execution | Finance Dept
30 | Quiet Period | 2019-12-26 08:00 | 2020-02-19 17:00 |  | No | 0%
31 | First Day of Public Trading | 2020-02-20 08:00 | 2020-02-20 17:00 |  | Yes | 0% | Execution | Board of Directors
32 | Second Quiet Period | 2020-02-21 08:00 | 2020-04-16 17:00 |  | No | 0% | Execution | Finance Dept
33 | Research Coverage Begins | 2020-04-17 08:00 | 2020-04-17 17:00 |  | Yes | 0% | Execution | Senior Mgt
34 | Issue First Earnings Forecast | 2020-04-17 08:00 | 2020-04-17 17:00 |  | Yes | 0% | Execution | Finance Dept