## Airport Master Plan
Task Name | Duration | Start Date | End Date | OnePager | Predecessors | Assigned To | OnePager
Short-Term | 3224d | 2010-08-26 | 2023-01-03
Airfield | 785d | 2020-01-01 | 2023-01-03
Additional Runway (7th) | 785d | 2020-01-01 | 2023-01-03 | TRUE |  |  | TRUE
Terminal & Gates | 2481d | 2012-07-01 | 2021-12-31
12 New Gates - Concourse A | 916d | 2018-07-01 | 2021-12-31 | TRUE |  |  | TRUE
11 New Gates - Concourse B | 916d | 2018-07-01 | 2021-12-31 | TRUE |  |  | TRUE
16 New Gates - Concourse C | 916d | 2018-07-01 | 2021-12-31 | TRUE |  |  | TRUE
International Passenger Processing Expansion | 523d | 2020-01-01 | 2021-12-31 | TRUE |  |  | TRUE
Tram Expansion | 523d | 2019-01-01 | 2020-12-31 | TRUE |  |  | TRUE
Baggage System Upgrades | 523d | 2020-01-01 | 2021-12-31 | TRUE |  |  | TRUE
Expansion of passenger security screening | 523d | 2020-01-01 | 2021-12-31 | TRUE |  |  | TRUE
Great Hall Project | 1045d | 2018-01-01 | 2021-12-31 | TRUE |  |  | TRUE
Westin Hotel | 850d | 2012-07-01 | 2015-10-01 | TRUE |  |  | TRUE
Transportation & Parking | 1593d | 2010-08-26 | 2016-10-03
Commuter Rail Line & Terminal Station | 1477d | 2010-08-26 | 2016-04-22 | TRUE |  |  | TRUE
Additional Parking Garage | 417d | 2015-03-01 | 2016-10-03 | TRUE |  |  | TRUE
Long-Term | 4175d | 2022-01-01 | 2037-12-31
Airfield | 4175d | 2022-01-01 | 2037-12-31
Additional Runway (8th) | 782d | 2027-01-01 | 2029-12-31 | TRUE |  |  | TRUE
Additional Runway (9th) | 784d | 2030-01-01 | 2032-12-31 | TRUE |  |  | TRUE
Additional Runway (10th) | 784d | 2035-01-01 | 2037-12-31 | TRUE |  |  | TRUE
Taxiway improvements | 4175d | 2022-01-01 | 2037-12-31 | TRUE |  |  | TRUE
More deicing positions | 523d | 2024-01-01 | 2025-12-31 | TRUE |  |  | TRUE
Terminal & Gates | 4175d | 2022-01-01 | 2037-12-31
50 New Gates - Addition of Concourse D | 1566d | 2022-01-01 | 2027-12-31 | TRUE |  |  | TRUE
50 New Gates - Addition of Concourse E | 1566d | 2032-01-01 | 2037-12-31 | TRUE |  |  | TRUE
International Passenger Processing Expansion | 522d | 2029-01-01 | 2030-12-31 | TRUE |  |  | TRUE
Expansion of passenger security screening | 522d | 2029-01-01 | 2030-12-31 | TRUE |  |  | TRUE
Transportation & Parking | 2870d | 2027-01-01 | 2037-12-31
Rental Car Facility Expansion | 784d | 2035-01-01 | 2037-12-31 | TRUE |  |  | TRUE
Fourth lane on Peña Boulevard | 782d | 2027-01-01 | 2029-12-31 | TRUE |  |  | TRUE
Public and employee parking expansion (near doubling) | 783d | 2032-01-01 | 2035-01-01 | TRUE |  |  | TRUE