## Sheet1
ID | Task Name | Start Date | Finish Date | Timeframe | Category
1 | Additional Runway (7th) | 2020-01-01 | 2022-12-31 | Short-Term | Airfield
2 | 12 New Gates - Concourse A | 2018-07-01 | 2021-12-31 | Short-Term | Terminal & Gates
3 | 11 New Gates - Concourse B | 2018-07-01 | 2021-12-31 | Short-Term | Terminal & Gates
4 | 16 New Gates - Concourse C | 2018-07-01 | 2021-12-31 | Short-Term | Terminal & Gates
5 | International Passenger Processing Expansion | 2020-01-01 | 2021-12-31 | Short-Term | Terminal & Gates
6 | Tram Expansion | 2019-01-01 | 2020-12-31 | Short-Term | Terminal & Gates
7 | Baggage System Upgrades | 2020-01-01 | 2021-12-31 | Short-Term | Terminal & Gates
8 | Expansion of passenger security screening | 2020-01-01 | 2021-12-31 | Short-Term | Terminal & Gates
9 | Great Hall Project | 2018-01-01 | 2021-12-31 | Short-Term | Terminal & Gates
10 | Commuter Rail Line & Terminal Station | 2010-08-26 | 2016-04-22 | Short-Term | Transportation & Parking
11 | Westin Hotel | 2012-07-01 | 2015-10-01 | Short-Term | Terminal & Gates
12 | Additional Parking Garage | 2015-03-01 | 2016-10-01 | Short-Term | Transportation & Parking
13 | Additional Runway (8th) | 2027-01-01 | 2029-12-31 | Long-Term | Airfield
14 | Additional Runway (9th) | 2030-01-01 | 2032-12-31 | Long-Term | Airfield
15 | Additional Runway (10th) | 2035-01-01 | 2037-12-31 | Long-Term | Airfield
16 | 50 New Gates - Addition of Concourse D | 2022-01-01 | 2027-12-31 | Long-Term | Terminal & Gates
17 | 50 New Gates - Addition of Concourse E | 2032-01-01 | 2037-12-31 | Long-Term | Terminal & Gates
18 | International Passenger Processing Expansion | 2029-01-01 | 2030-12-31 | Long-Term | Terminal & Gates
19 | Expansion of passenger security screening | 2029-01-01 | 2030-12-31 | Long-Term | Terminal & Gates
20 | Taxiway improvements | 2022-01-01 | 2037-12-31 | Long-Term | Airfield
21 | More deicing positions | 2024-01-01 | 2025-12-31 | Long-Term | Airfield
22 | Rental Car Facility Expansion | 2035-01-01 | 2037-12-31 | Long-Term | Transportation & Parking
23 | Fourth lane on Peña Boulevard | 2027-01-01 | 2029-12-31 | Long-Term | Transportation & Parking
24 | Public and employee parking expansion (near doubling) | 2032-01-01 | 2034-12-31 | Long-Term | Transportation & Parking