## Sheet1
UID | Stage | Product | Line of Business | Start Date | Duration | Finish Date
1 | Planning | Twidge | Consumer | 2022-10-27 | 268 | 2023-07-22
2 | Design | Twidge | Consumer | 2023-07-23 | 331 | 2024-06-18
3 | Prototype | Twidge | Consumer | 2024-06-19 | 296 | 2025-04-11
4 | Design for Manufacturing | Twidge | Consumer | 2025-04-12 | 234 | 2025-12-02
5 | Manufacturing | Twidge | Consumer | 2025-12-03 | 163 | 2026-05-15
6 | Post-Manufacturing | Twidge | Consumer | 2026-05-16 | 284 | 2027-02-24
7 | Planning | Maculats | Consumer | 2022-07-12 | 238 | 2023-03-07
8 | Design | Maculats | Consumer | 2023-03-08 | 359 | 2024-03-01
9 | Prototype | Maculats | Consumer | 2024-03-02 | 263 | 2024-11-20
10 | Design for Manufacturing | Maculats | Consumer | 2024-11-21 | 364 | 2025-11-20
11 | Manufacturing | Maculats | Consumer | 2025-11-21 | 331 | 2026-10-18
12 | Post-Manufacturing | Maculats | Consumer | 2026-10-19 | 173 | 2027-04-10
13 | Planning | Moldirs | Consumer | 2021-07-05 | 321 | 2022-05-22
14 | Design | Moldirs | Consumer | 2022-05-23 | 242 | 2023-01-20
15 | Prototype | Moldirs | Consumer | 2023-01-21 | 197 | 2023-08-06
16 | Design for Manufacturing | Moldirs | Consumer | 2023-08-07 | 225 | 2024-03-19
17 | Manufacturing | Moldirs | Consumer | 2024-03-20 | 147 | 2024-08-14
18 | Post-Manufacturing | Moldirs | Consumer | 2024-08-15 | 135 | 2024-12-28
19 | Planning | Overtaxez | Consumer | 2021-06-08 | 351 | 2022-05-25
20 | Design | Overtaxez | Consumer | 2022-05-26 | 121 | 2022-09-24
21 | Prototype | Overtaxez | Consumer | 2022-09-25 | 194 | 2023-04-07
22 | Design for Manufacturing | Overtaxez | Consumer | 2023-04-08 | 142 | 2023-08-28
23 | Manufacturing | Overtaxez | Consumer | 2023-08-29 | 158 | 2024-02-03
24 | Post-Manufacturing | Overtaxez | Consumer | 2024-02-04 | 348 | 2025-01-17
25 | Planning | Finits | Commercial | 2021-07-30 | 271 | 2022-04-27
26 | Design | Finits | Commercial | 2022-04-28 | 266 | 2023-01-19
27 | Prototype | Finits | Commercial | 2023-01-20 | 93 | 2023-04-23
28 | Design for Manufacturing | Finits | Commercial | 2023-04-24 | 139 | 2023-09-10
29 | Manufacturing | Finits | Commercial | 2023-09-11 | 328 | 2024-08-04
30 | Post-Manufacturing | Finits | Commercial | 2024-08-05 | 273 | 2025-05-05
31 | Planning | Tracably | Commercial | 2022-03-31 | 116 | 2022-07-25
32 | Design | Tracably | Commercial | 2022-07-26 | 225 | 2023-03-08
33 | Prototype | Tracably | Commercial | 2023-03-09 | 273 | 2023-12-07
34 | Design for Manufacturing | Tracably | Commercial | 2023-12-08 | 132 | 2024-04-18
35 | Manufacturing | Tracably | Commercial | 2024-04-19 | 100 | 2024-07-28
36 | Post-Manufacturing | Tracably | Commercial | 2024-07-29 | 278 | 2025-05-03
37 | Planning | Kadenced | Commercial | 2021-01-02 | 186 | 2021-07-07
38 | Design | Kadenced | Commercial | 2021-07-08 | 101 | 2021-10-17
39 | Prototype | Kadenced | Commercial | 2021-10-18 | 244 | 2022-06-19
40 | Design for Manufacturing | Kadenced | Commercial | 2022-06-20 | 265 | 2023-03-12
41 | Manufacturing | Kadenced | Commercial | 2023-03-13 | 350 | 2024-02-26
42 | Post-Manufacturing | Kadenced | Commercial | 2024-02-27 | 364 | 2025-02-25
43 | Planning | Rokkingham | Commercial | 2021-02-06 | 143 | 2021-06-29
44 | Design | Rokkingham | Commercial | 2021-06-30 | 195 | 2022-01-11
45 | Prototype | Rokkingham | Commercial | 2022-01-12 | 169 | 2022-06-30
46 | Design for Manufacturing | Rokkingham | Commercial | 2022-07-01 | 173 | 2022-12-21
47 | Manufacturing | Rokkingham | Commercial | 2022-12-22 | 300 | 2023-10-18
48 | Post-Manufacturing | Rokkingham | Commercial | 2023-10-19 | 286 | 2024-07-31