## Agile Project Schedule
Task Name | Duration | Start Date | End Date | Predecessors | % Complete | Status | Assigned To | Comments | Text1 | Text2 | Add to OnePager
Overall Project | 29d | 2024-05-20 | 2024-06-27 |  | 0% |  | ScrumMaster |  | Planning - Ongoing | Planning | TRUE
Mtg 1 | 1d | 2024-05-20 | 2024-05-20 |  | 0% |  | ScrumMaster |  | Planning - Ongoing | Planning | TRUE
Mtg 2 | 1d | 2024-05-23 | 2024-05-23 |  | 0% |  | ScrumMaster |  | Planning - Ongoing | Planning | TRUE
Mtg 3 | 1d | 2024-05-30 | 2024-05-30 |  | 0% |  | ScrumMaster |  | Planning - Ongoing | Planning | TRUE
Mtg 4 | 1d | 2024-06-06 | 2024-06-06 |  | 0% |  | ScrumMaster |  | Planning - Ongoing | Planning | TRUE
Mtg 5 | 1d | 2024-06-13 | 2024-06-13 |  | 0% |  | ScrumMaster |  | Planning - Ongoing | Planning | TRUE
Every other week Sprint Planning | 26d | 2024-05-23 | 2024-06-27 |  | 0% |  | ScrumMaster |  | Planning 1 - Ongoing | Planning | TRUE
Sprint 1 | 1d | 2024-05-23 | 2024-05-23 |  | 0% |  | ScrumMaster |  | Planning 1 - Ongoing | Sprint 1 | TRUE
Sprint 2 | 1d | 2024-06-12 | 2024-06-12 |  | 0% |  | ScrumMaster |  | Planning 1 - Ongoing | Sprint 2 | TRUE
Sprint 3 | 1d | 2024-06-27 | 2024-06-27 |  | 0% |  | ScrumMaster |  | Planning 1 - Ongoing | Sprint 3 | TRUE
Sprint 1 | 14d | 2024-05-24 | 2024-06-12 |  | 0% |  | Sprint 1 Team |  | Sprint 1 - Ongoing | Sprint 1 | TRUE
Standups | 10d | 2024-05-24 | 2024-06-06 |  | 0% |  | Sprint 1 Team |  | Sprint 1 - Ongoing | Sprint 1
Mtg 1 | 1d | 2024-05-24 | 2024-05-24 |  | 0% |  | Sprint 1 Team |  | Sprint 1 - Ongoing | Sprint 1 | TRUE
Mtg 2 | 1d | 2024-05-27 | 2024-05-27 |  | 0% |  | Sprint 1 Team |  | Sprint 1 - Ongoing | Sprint 1 | TRUE
Mtg 3 | 1d | 2024-05-30 | 2024-05-30 |  | 0% |  | Sprint 1 Team |  | Sprint 1 - Ongoing | Sprint 1 | TRUE
Mtg 4 | 1d | 2024-06-03 | 2024-06-03 |  | 0% |  | Sprint 1 Team |  | Sprint 1 - Ongoing | Sprint 1 | TRUE
Mtg 5 | 1d | 2024-06-06 | 2024-06-06 |  | 0% |  | Sprint 1 Team |  | Sprint 1 - Ongoing | Sprint 1 | TRUE
Retrospective | 1d | 2024-06-12 | 2024-06-12 |  | 0% |  | Sprint 1 Team |  | Sprint 1 - Ongoing | Sprint 1 | TRUE
Sprint 2 | 12d | 2024-06-12 | 2024-06-27 |  | 0% |  | Sprint 2 Team |  | Sprint 2 - Ongoing | Sprint 2 | TRUE
Standups | 12d | 2024-06-12 | 2024-06-27 |  | 0% |  | Sprint 2 Team |  | Sprint 2 - Ongoing | Sprint 2
Mtg 1 | 1d | 2024-06-12 | 2024-06-12 |  | 0% |  | Sprint 2 Team |  | Sprint 2 - Ongoing | Sprint 2 | TRUE
Mtg 2 | 1d | 2024-06-14 | 2024-06-14 |  | 0% |  | Sprint 2 Team |  | Sprint 2 - Ongoing | Sprint 2 | TRUE
Mtg 3 | 1d | 2024-06-17 | 2024-06-17 |  | 0% |  | Sprint 2 Team |  | Sprint 2 - Ongoing | Sprint 2 | TRUE
Mtg 4 | 1d | 2024-06-19 | 2024-06-19 |  | 0% |  | Sprint 2 Team |  | Sprint 2 - Ongoing | Sprint 2 | TRUE
Mtg 5 | 1d | 2024-06-21 | 2024-06-21 |  | 0% |  | Sprint 2 Team |  | Sprint 2 - Ongoing | Sprint 2 | TRUE
Retro. | 1d | 2024-06-27 | 2024-06-27 |  | 0% |  | Sprint 2 Team |  | Sprint 2 - Ongoing | Sprint 2 | TRUE